## Reference (hidden)
Task Type
Development
Documentation
Meeting
Modeling
Presentation
Research
Process
Design
Testing
Planning

## Totals
Name | EST Total | ACT Total
Matt | 292.875 | 320.125
Daniel | 260.5 | 317
Aaron | 146.25 | 210.5
Philip | 241 | 291.75
Term 1
Name | Term 1 EST Total | Term 1 ACT Total | T1 Wk 01 EST | T1 Wk 01 ACT | T1 Wk 02 EST | T1 Wk 02 ACT | T1 Wk 03 EST | T1 Wk 03 ACT | T1 Wk 04 EST | T1 Wk 04 ACT | T1 Wk 05 EST | T1 Wk 05 ACT | T1 Wk 06 EST | T1 Wk 06 ACT | T1 Wk 07 EST | T1 Wk 07 ACT | T1 Wk 08 EST | T1 Wk 08 ACT | T1 Wk 09 EST | T1 Wk 09 ACT | T1 Wk 10 EST | T1 Wk 10 ACT | T1 Wk 11 EST | T1 Wk 11 ACT | T1 Wk 12 EST | T1 Wk 12 ACT | T1 Wk 13 EST | T1 Wk 13 ACT | T1 Wk 14 EST | T1 Wk 14 ACT | T1 Wk 15 EST | T1 Wk 15 ACT
Matt | 72.375 | 73.875 | 1.5 | 1.5 | 5.875 | 5.875 | 8.5 | 12.5 | 8.75 | 9.5 | 2.75 | 2.75 | 3.5 | 3.5 | 9.5 | 8.25 | 8.5 | 9 | 7 | 6.5 | 2.25 | 2.25 | 5 | 4.75 | 4 | 3.25 | 1 | 1 | 4.25 | 3.25 | 0 | 0
Daniel | 91 | 102.5 | 2 | 7 | 5.25 | 6.25 | 2.75 | 2.75 | 16 | 14.5 | 4.5 | 5.5 | 6.5 | 8.5 | 8.5 | 7.5 | 3.5 | 3.5 | 9.5 | 9.5 | 9.5 | 7.5 | 4.5 | 8.5 | 9.5 | 10.5 | 3 | 3 | 6 | 8 | 0 | 0
Aaron | 75.25 | 96.75 | 4 | 6 | 5.75 | 6.75 | 4.5 | 6.5 | 2 | 2 | 4 | 5 | 5 | 5 | 2 | 3 | 5 | 5 | 2 | 2 | 8 | 11 | 9 | 11.75 | 8 | 9.75 | 7 | 11 | 9 | 12 | 0 | 0
Philip | 78.5 | 90.5 | 3 | 7 | 8 | 6 | 10 | 11 | 6 | 6 | 6 | 5.5 | 8 | 9 | 8 | 7.5 | 4 | 5 | 5 | 5 | 3 | 3 | 10.5 | 11 | 3 | 5 | 2 | 6 | 2 | 3.5 | 0 | 0
Term 2
Name | Term 2 EST Total | Term 2 ACT Total | T2 Wk 01 EST | T2 Wk 01 ACT | T2 Wk 02 EST | T2 Wk 02 ACT | T2 Wk 03 EST | T2 Wk 03 ACT | T2 Wk 04 EST | T2 Wk 04 ACT | T2 Wk 05 EST | T2 Wk 05 ACT | T2 Wk 06 EST | T2 Wk 06 ACT | T2 Wk 07 EST | T2 Wk 07 ACT | T2 Wk 08 EST | T2 Wk 08 ACT | T2 Wk 09 EST | T2 Wk 09 ACT | T2 Wk 10 EST | T2 Wk 10 ACT | T2 Wk 11 EST | T2 Wk 11 ACT | T2 Wk 12 EST | T2 Wk 12 ACT | T2 Wk 13 EST | T2 Wk 13 ACT | T2 Wk 14 EST | T2 Wk 14 ACT | T2 Wk 15 EST | T2 Wk 15 ACT
Matt | 220.5 | 246.25 | 4.25 | 4.75 | 19.5 | 16.75 | 9.5 | 10.25 | 9 | 6 | 6.5 | 10.5 | 17.5 | 23.5 | 8.25 | 14.25 | 8.5 | 10.75 | 19 | 16.75 | 22.5 | 21.25 | 36.5 | 44.75 | 23.5 | 22.25 | 26 | 37.5 | 10 | 7 | 0 | 0
Daniel | 169.5 | 214.5 | 5 | 10 | 10 | 12 | 6 | 13 | 13 | 8 | 6 | 10 | 27 | 30 | 23 | 27 | 10 | 14.5 | 15.5 | 15.5 | 13 | 13 | 13 | 19.5 | 12 | 17 | 14 | 23 | 2 | 2 | 0 | 0
Aaron | 71 | 113.75 | 5 | 7.5 | 4 | 5 | 2 | 5 | 3 | 3 | 4 | 5 | 11 | 12 | 5 | 6.5 | 3 | 6 | 3 | 6 | 12 | 22 | 9 | 9.75 | 5 | 14 | 3 | 9 | 2 | 3 | 0 | 0
Philip | 162.5 | 201.25 | 2 | 1.5 | 22 | 21.25 | 8 | 8.5 | 12 | 10 | 6 | 7.5 | 16 | 20.5 | 16 | 11.75 | 8.5 | 8.75 | 10 | 13.5 | 17 | 27.5 | 13 | 18 | 13 | 14.5 | 19 | 38 | 0 | 0 | 0 | 0

## Matt
Task | Task Type | EST | ACT | Term | Week | Done
Initial Team Meet-up in the auditorium with Kal | Meeting | 0.5 | 0.5 | 1 | 1 | TRUE
Kick-Off Meeting 8/30/18 | Meeting | 1 | 1 | 1 | 1 | TRUE
Set up AWS account | Process | 0.125 | 0.125 | 1 | 2 | TRUE
Team Meeting 9/4/19 - Discussed Requirements and what the software should actually do. Discussed methodology. Discussed Cloud solutions. | Meeting | 1.5 | 1.5 | 1 | 2 | TRUE
Designed Low Fidelity Wireframe to show what functionality we *thought* the software was going to have and get feedback | Modeling | 1.5 | 1.5 | 1 | 2 | TRUE
Team Meeting 9/6/19 - Started Requirements Documentation, Assigned Team Roles, Selected Design Methodology | Meeting | 1.25 | 1.25 | 1 | 2 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 2 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 2 | TRUE
Team Meeting 9/11/18 - Went over research, conitnued requirements documentation work | Meeting | 1.25 | 1.25 | 1 | 3 | TRUE
Opened a LucidChart Folder for our Modeling documents and shared access with team (Matt) | Documentation | 0.25 | 0.25 | 1 | 3 | TRUE
Added the Domain Models in to LucidChart (Matt) | Modeling | 0.5 | 0.5 | 1 | 3 | TRUE
Worked on Project Website (Matt) | Documentation | 1 | 2 | 1 | 3 | TRUE
Re-wrote hour tracking log for google sheets (Matt) | Process | 3 | 6 | 1 | 3 | TRUE
Formatted 4-Up Charts, Requirements Document, Use Cases | Process | 1 | 1 | 1 | 3 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 3 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 3 | TRUE
7 Sequence Diagrams: login, approve/deny, add acct owner, add domain, view open content, view my requests, create content | Modeling | 4 | 4 | 1 | 4 | TRUE
Research UI Design and Best Practices | Research | 10 |  | 1 | 4 | FALSE
Got team website up and running | Process | 0.25 | 0.5 | 1 | 4 | TRUE
Wrote a python script to put links to public_html documents in to an html list | Process | 1.5 | 1.5 | 1 | 4 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 4 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 4 | TRUE
Set up team account and gained access (had to talk to IT) | Process | 0.5 | 1 | 1 | 4 | TRUE
Figured out a flow to get google documents to SE project website | Research | 1 | 1 | 1 | 4 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 5 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 5 | TRUE
Review Domain Model | Modeling | 0.5 | 0.5 | 1 | 5 | TRUE
Review Use Case Documents | Documentation | 0.75 | 0.75 | 1 | 5 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 6 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 6 | TRUE
Add project plan to Google Site, link to SE team site | Documentation | 0.5 | 0.5 | 1 | 6 | TRUE
Condensed Four-Up Charts back down to weekly charts | Documentation | 0.5 | 0.5 | 1 | 6 | TRUE
Add Software Engineering Timeline deliverables to Project Plan | Documentation | 1 | 1 | 1 | 6 | TRUE
Database ERD | Modeling | 2 | 1.5 | 1 | 7 | TRUE
Database Reduction to Tables | Modeling | 1 | 0.75 | 1 | 7 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 7 | TRUE
Created Gantt Chart - Styled Schedule in Google Sheets | Process | 4 | 4 | 1 | 7 | TRUE
Updated Bizcloud Website | Documentation | 2 | 1.5 | 1 | 7 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 8 | TRUE
Web App UI Mockup | Design | 3 | 4 | 1 | 8 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 8 | TRUE
Created ERD as well as looked back at DB Architecture and determine what tech to use | Modeling | 4 | 3.5 | 1 | 8 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 9 | TRUE
Web App UI Mockup Version 2 | Design | 4 | 4 | 1 | 9 | TRUE
Database ERD Update | Modeling | 1 | 1 | 1 | 9 | TRUE
Database Reduction to Tables Update | Modeling | 1 | 1 | 1 | 9 | TRUE
Team Meeting | Process | 0.5 | 0 | 1 | 9 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 10 | TRUE
Mid-Term project review with Kal | Meeting | 1 | 1 | 1 | 10 | TRUE
Update Project Website | Process | 0.25 | 0.25 | 1 | 10 | TRUE
Team Meeting | Process | 0.5 | 0.5 | 1 | 10 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 11 | TRUE
Team Meeting | Meeting | 1 | 1 | 1 | 11 | TRUE
Updated Requirements Doc | Documentation | 0.5 | 0.5 | 1 | 11 | TRUE
Some Researching of UI and Design best practices for Smart TV display | Research | 1 | 0.75 | 1 | 11 | TRUE
Group Meeting to explore technologies | Meeting | 2 | 2 | 1 | 11 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 12 | TRUE
Update Project Website | Process | 0.25 | 0.25 | 1 | 12 | TRUE
Updated Project Plan | Process | 1 | 0.75 | 1 | 12 | TRUE
Updated ERD | Process | 0.5 | 0.25 | 1 | 12 | TRUE
Updated Project Schedule | Process | 0.5 | 0.5 | 1 | 12 | TRUE
Updated Table Reduction | Process | 0.25 | 0.25 | 1 | 12 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 0.75 | 1 | 12 | TRUE
Added Use Case for registering account | Documentation | 0.5 | 0.5 | 1 | 13 | TRUE
Reviewed Use Case Document; edited Use Case for registering smart TV and Pushing Content | Documentation | 0.5 | 0.5 | 1 | 13 | TRUE
Update Project Website | Process | 0.25 | 0.25 | 1 | 14 | TRUE
Work on Project Presentation | Presentation | 4 | 3 | 1 | 14 | TRUE
FALSE
Team Meeting | Meeting | 1.5 | 1.25 | 2 | 1 | TRUE
Reserve Team Room in Library for Tuesday Meeting | Process | 0.125 | 0.125 | 2 | 1 | TRUE
Email Bizcloud with Redmine and Phil's permission requests | Process | 0.125 | 0.125 | 2 | 1 | TRUE
Review meeting notes, delegate actions | Process | 0.5 | 0.75 | 2 | 1 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1.5 | 2 | 1 | TRUE
Sprint Planning | Meeting | 1 | 1 | 2 | 1 | TRUE
Fill out descriptions and Acceptance Criteria for Sprint 5 | Process | 1 | 1 | 2 | 2 | TRUE
Update JIRA to reflect project plan schedule | Process | 2.5 | 0.5 | 2 | 2 | TRUE
Create Google Calendar with sprint plans, meetings, due dates, etc. to map out the rest of the semester | Process | 5 | 1.5 | 2 | 4 | TRUE
Update all currently entered use cases in the use case document | Documentation | 6 | 6 | 2 | 2 | TRUE
Update sequence diagrams for currently implemented use cases | Modeling | 4 | 4 | 2 | 3 | TRUE
Team meeting with Kal | Meeting | 1 | 1.5 | 2 | 2 | TRUE
Update use case document to reflect all requirements | Documentation | 4 | 2 | 2 | 2 | TRUE
Update project plan to reflect changes to use case document | Documentation | 1 | 1 | 2 | 2 | TRUE
Team meeting with Bizcloud | Meeting | 1 | 1.5 | 2 | 2 | TRUE
Update project plan to reflect changes to features and sprint plan | Documentation | 1 | 0.75 | 2 | 2 | TRUE
Team sprint planning meeting | Meeting | 1 | 0.5 | 2 | 2 | TRUE
Team sprint planning meeting | Meeting | 1 | 2 | 2 | 2 | TRUE
Write out agendas for this week, check Jira, check 4-ups, update 4-up document | Planning | 1 | 0.75 | 2 | 3 | TRUE
Review feedback from Kal on Process document | Process | 0.5 | 0.5 | 2 | 3 | TRUE
Team sprint planning meeting | Meeting | 1 | 1 | 2 | 3 | TRUE
Team meeting with Bizcloud | Meeting | 1 | 1 | 2 | 3 | TRUE
Team meeting | Meeting | 1 | 2 | 2 | 3 | TRUE
Update project plan from sequence diagrams | Documentation | 1 | 1 | 2 | 3 | TRUE
Update Jira with all use cases and reflect the project plan | Planning | 3 | 3 | 2 | 5 | TRUE
Team meeting | Meeting | 1 | 1.5 | 2 | 4 | TRUE
Team meeting with Bizcloud and Demo | Meeting | 1 | 1.5 | 2 | 4 | TRUE
Updated Jira with descriptions | Planning | 1 | 1 | 2 | 4 | TRUE
Look in to UI solutions | Research | 1 | 0.5 | 2 | 4 | TRUE
Remote team meeting | Meeting | 1 | 1.5 | 2 | 5 | TRUE
Worked on implementing Client list and creation | Development | 1.5 | 3.5 | 2 | 5 | TRUE
Meeting with Bizcloud | Meeting | 1 | 2.5 | 2 | 5 | TRUE
Team Meeting | Meeting | 1 | 2 | 2 | 6 | TRUE
Work on Jira | Planning | 2 | 3.5 | 2 | 6 | TRUE
Testing for Sprint 6 | Testing | 2 | 1 | 2 | 6 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1.5 | 2 | 6 | TRUE
Agenda for both meetings | Planning | 1 | 0.75 | 2 | 6 | TRUE
Four-up Update | Planning | 0.5 | 0.5 | 2 | 6 | TRUE
Coding day | Development | 5 | 1.25 | 2 | 6 | TRUE
Implement adding new section | Development | 3 | 9 | 2 | 6 | TRUE
Draw up wireframes | Modeling | 2 | 4 | 2 | 6 | TRUE
Fix a few things in adding new section and add some more UI elements / robustness | Development | 2 | 3 | 2 | 7 | TRUE
Team Meeting | Meeting | 1 | 1.25 | 2 | 7 | TRUE
Fix bugs | Development | 1 | 1.5 | 2 | 7 | TRUE
Sprint 7 Testing | Testing | 1 | 0.75 | 2 | 7 | TRUE
UI Overhaul / Fix section error | Development | 1 | 3 | 2 | 7 | TRUE
Fill in Jira descriptions / AC for Sprint 8 | Planning | 1 | 2 | 2 | 7 | TRUE
Update SE website | Process | 0.25 | 0.25 | 2 | 7 | TRUE
Sponsor Meeting / Demo | Meeting | 1 | 2.5 | 2 | 7 | TRUE
Poster presentation | Meeting | 1 | 0.75 | 2 | 8 | TRUE
Material Ramp-Up | Research | 2 | 2 | 2 | 8 | TRUE
Get ready for Thursday Sponsor Meeting | Planning | 1 | 0.5 | 2 | 8 | TRUE
Thursday Sponsor Meeting | Meeting | 1 | 1.5 | 2 | 8 | TRUE
Content Submission Flow | Design | 1 | 3 | 2 | 8 | TRUE
SP - 377 Elaborate on Tests and make sure they're in similar formats | Testing | 1 | 1.5 | 2 | 8 | TRUE
Organize some things on jira | Process | 0.5 | 0.5 | 2 | 8 | TRUE
Look in to other team's websites | Research | 1 | 1 | 2 | 8 | TRUE
Add more functional testing for SP - 377 | Testing | 2 | 0.75 | 2 | 9 | TRUE
Finish write-up for Website content | Design | 1 | 1 | 2 | 9 | TRUE
Wireframe / Design for SE Website | Design | 2 | 3.5 | 2 | 9 | TRUE
Fill in Jira descriptions / AC and Plan for Sprint 9 | Planning | 2 | 2 | 2 | 9 | TRUE
Finish Sprint 8 Test Plan new tests | Testing | 1 | 1 | 2 | 9 | TRUE
Updated Jira and listed out pointing for Sprint 9 | Planning | 1 | 0.5 | 2 | 9 | TRUE
Build out SE Project Website | Documentation | 10 | 8 | 2 | 9 | TRUE
Materialize Landing Page and Login Page and add logout button to Navbar (twice...) | Documentation | 3 | 3 | 2 | 10 | TRUE
Transfer files over to Team Drive | Documentation | 2 | 2 | 2 | 10 | TRUE
Point stories | Planning | 0.5 | 0.5 | 2 | 10 | TRUE
Review Phil's PR | Testing | 0.5 | 0.5 | 2 | 10 | TRUE
Team meeting | Meeting | 0.75 | 1.5 | 2 | 10 | TRUE
Planning, Four-Up updates | Planning | 0.75 | 1.25 | 2 | 10 | TRUE
Testing | Testing | 1 | 1.5 | 2 | 10 | TRUE
Finish writing up content submission flow document | Design | 0.25 | 0.25 | 2 | 10 | TRUE
sponsor meeting | Meeting | 1 | 1.75 | 2 | 10 | TRUE
Fix redirect not working on device approval bug | Development | 0.5 | 0.5 | 2 | 10 | TRUE
Work on SE Website | Development | 8 | 2 | 2 | 10 | TRUE
Setting up local environment to deploy lambdas | Development | 0.25 | 1 | 2 | 10 | TRUE
Work session | Meeting | 4 | 5.5 | 2 | 10 | TRUE
Working on getting the list of content requests finished | Development | 6 | 9 | 2 | 11 | TRUE
Materialized client entry and list | Development | 5 | 3.5 | 2 | 11 | TRUE
Project Review with Kal | Meeting | 1 | 1 | 2 | 11 | TRUE
Team meeting | Meeting | 1 | 0.75 | 2 | 11 | TRUE
Updated Bizcloud project website | Process | 1 | 0.5 | 2 | 11 | TRUE
Worked on website (had to rename everything to work properly with casing on Apache (python on windows didn't care)) | Development | 1 | 3 | 2 | 11 | TRUE
SE Website work, added some content, did some refactoring, adding files | Development | 3 | 4 | 2 | 11 | TRUE
Process Documentation | Documentation | 1 | 3 | 2 | 11 | TRUE
More work on creating assets for the SE website as well as adding to the document list | Development | 4 | 6 | 2 | 11 | TRUE
Fixed angular reload issue with materialized content list / quick functional tests / quick UI update | Development | 1 | 0.5 | 2 | 11 | TRUE
Update documentation | Documentation | 1 | 1 | 2 | 11 | TRUE
Finish up most work on SE Website | Development | 1 | 3 | 2 | 11 | TRUE
Planning for meeting | Planning | 0.5 | 0.5 | 2 | 11 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1.5 | 2 | 11 | TRUE
Work on poster | Presentation | 6 | 4 | 2 | 11 | TRUE
Sprint 10 Planning | Planning | 2 | 2.5 | 2 | 11 | TRUE
Sprint 9 Testing | Testing | 1 | 1 | 2 | 11 | TRUE
Planning | Planning | 1 | 1.75 | 2 | 12 | TRUE
Work on Poster | Presentation | 5 | 3 | 2 | 12 | TRUE
Update Documentation | Documentation | 0.5 | 0.5 | 2 | 12 | TRUE
Project Review with Kal pt. 2 | Meeting | 1 | 1 | 2 | 12 | TRUE
Reformat the poster | Presentation | 4 | 2 | 2 | 12 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1 | 2 | 12 | TRUE
Working on page omission in the app depending on the user logged in | Development | 5 | 7 | 2 | 12 | TRUE
Omit pages from being viewed depending on the user logged in | Development | 6 | 6 | 2 | 12 | TRUE
Materialize device list and add a list of content currently deployed to a specific devices | Development | 5 | 5 | 2 | 13 | TRUE
Make lists only display user-relevant items based on client or account | Development | 3 | 3 | 2 | 13 | TRUE
Team Meeting to hash out some work and go over demo | Meeting | 1 | 2 | 2 | 13 | TRUE
Work on Jira | Planning | 1 | 1 | 2 | 13 | TRUE
Continue working on development tasks | Development | 8 | 15 | 2 | 13 | TRUE
Meeting with Bizcloud and plan final sprint | Meeting | 1 | 2 | 2 | 13 | TRUE
Planning for meeting | Planning | 1 | 1 | 2 | 13 | TRUE
Update metrics documentation | Process | 1 | 2 | 2 | 13 | TRUE
Work on poster | Presentation | 2 | 4.5 | 2 | 13 | TRUE
Work on Jira | Process | 1 | 1 | 2 | 13 | TRUE
Bug fixes | Development | 2 | 1 | 2 | 13 | TRUE
Worked on poster | Presentation | 2 | 3 | 2 | 14 | TRUE
Worked on Final Presentation | Presentation | 4 | 2 | 2 | 14 | TRUE
Update documentation | Documentation | 2 | 1 | 2 | 14 | TRUE
Brief meeting with bizcloud | Meeting | 1 | 0.5 | 2 | 14 | TRUE
Write demo draft | Presentation | 1 | 0.5 | 2 | 14 | TRUE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 | 15 | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE
|  |  |  | 2 |  | FALSE

## Daniel
Task | Task Type | EST | ACT | Term | Week | Done
Attended a Meeting | Meeting | 1 | 3 | 1 | 1 | TRUE
Set Up AWS Account | Process | 1 | 4 | 1 | 1 | TRUE
Team Meeting 9/4/19 - Discussed Requirements and what the software should actually do. Discussed methodology. Discussed Cloud solutions. | Meeting | 1.5 | 1.5 | 1 | 2 | TRUE
Team Meeting 9/6/19 - Started Requirements Documentation, Assigned Team Roles, Selected Design Methodology | Meeting | 1.25 | 1.25 | 1 | 2 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 2 | TRUE
Work on project plan | Documentation | 1 | 2 | 1 | 2 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 2 | TRUE
Team Meeting 9/11/18 - Went over research, conitnued requirements documentation work | Meeting | 1.25 | 1.25 | 1 | 3 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 3 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 3 | TRUE
2 Sequence Diagrams: push content to a specific tv and approve a content request | Modeling | 2 | 2 | 1 | 4 | TRUE
Research AWS IOT | Research | 10 | 5 | 1 | 4 | TRUE
Set up local AWS CLI on local machines and run set up scripts on the AWS Account | Process | 1.5 | 4 | 1 | 4 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 4 | TRUE
Investigate what rights are needed for the AWS Account | Research | 1 | 2 | 1 | 4 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 4 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 5 | TRUE
Understand Bastion host, and AWS service catalog | Research | 3 | 4 | 1 | 5 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 5 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 6 | TRUE
AWS Serveless Web Application research | Research | 5 | 7 | 1 | 6 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 6 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 7 | TRUE
Design how to push Database update to web application | Design | 1 | 3 | 1 | 7 | TRUE
AWS API Gateway Research | Research | 7 | 4 | 1 | 7 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 8 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 8 | TRUE
Create Infrastructure Model to verify what services need to be spun up | Modeling | 2 | 2 | 1 | 8 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 9 | TRUE
AWS Cognito Research | Research | 5 | 4 | 1 | 9 | TRUE
Work with Karthik to get AWS infrastucture Model Approved | Design | 3 | 3 | 1 | 9 | TRUE
Implement changes to AWS infrastucture Model | Modeling | 1 | 2 | 1 | 9 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 10 | TRUE
Serverless Framework Research and Demoing | Research | 8 | 6 | 1 | 10 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 10 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 11 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 11 | TRUE
Establish Connection to RDS and reseach how to make queries to the SQL from lambda | Development | 2 | 6 | 1 | 11 | TRUE
Reseach what lambdas permisions will be needed for the webapp | Research | 1 | 1 | 1 | 11 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 12 | TRUE
Document what personal understandings of the system are | Documentation | 1 | 1 | 1 | 12 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 12 | TRUE
Work with Karthik to set up serverless lambda deployments and rds mysql connections when on rit vpn | Process | 2 | 2 | 1 | 12 | TRUE
Initial lambda implementation for the release one | Development | 5 | 6 | 1 | 12 | TRUE
Create Interim Presentation and work on it | Presentation | 3 | 3 | 1 | 13 | TRUE
Meet with Kal to discuss interim presentation | Meeting | 2 | 2 | 1 | 14 | TRUE
Work on presentation post Kal's updates | Presentation | 2 | 2.5 | 1 | 14 | TRUE
Meet to work on presentation | Presentation | 2 | 3.5 | 1 | 14 | TRUE
Meet to discuss start of semester | Meeting | 1 | 1 | 2 | 1 | TRUE
Set up jira | Research | 3 | 8 | 2 | 1 | TRUE
Review architecture Models | Modeling | 1 | 1 | 2 | 1 | TRUE
Work on test plan document | Documentation | 3 | 5 | 2 | 2 | TRUE
Set up AWS Cognitio | Development | 4 | 4 | 2 | 2 | TRUE
Group Meetings week 2 | Meeting | 3 | 3 | 2 | 2 | TRUE
Work on Test Plan Jira | Process | 2 | 4 | 2 | 3 | TRUE
Group meetings week 3 | Meeting | 3 | 6 | 2 | 3 | TRUE
Trouble shooting content cors error | Development | 1 | 3 | 2 | 3 | TRUE
Work on account representation | Development | 10 | 5 | 2 | 4 | TRUE
group meetings week 4 | Meeting | 3 | 3 | 2 | 4 | TRUE
group meetings week 5 | Meeting | 3 | 4 | 2 | 5 | TRUE
work on account representation/test in account and plan future work | Development | 3 | 6 | 2 | 5 | TRUE
Work on edit lambda implementation | Development | 5 | 7 | 2 | 6 | TRUE
Implement unit tests for all existing lambdas | Development | 8 | 10 | 2 | 6 | TRUE
Create webapp login page ui wireframe | Design | 2 | 2 | 2 | 6 | TRUE
Create Devices Wireframes | Design | 5 | 4 | 2 | 6 | TRUE
Saturday meeting | Meeting | 4 | 4 | 2 | 6 | TRUE
group meetings week 6 | Meeting | 3 | 3 | 2 | 6 | TRUE
Android App architecture Research | Research | 2 | 4 | 2 | 7 | TRUE
Implement android id | Development | 4 | 3 | 2 | 7 | TRUE
Implement CD on github | Development | 3 | 6 | 2 | 7 | TRUE
Bug fix for device linking | Development | 1 | 1 | 2 | 7 | TRUE
Testing for sprint 7 | Testing | 1 | 1 | 2 | 7 | TRUE
Work on cards in android tv | Development | 2 | 2 | 2 | 7 | TRUE
implement device status | Development | 2 | 2 | 2 | 7 | TRUE
Implement CI on Lambdas | Development | 3 | 3 | 2 | 7 | TRUE
implement dynamic device topic (untested) | Development | 3 | 3 | 2 | 7 | TRUE
set up github slack integration | Process | 1 | 1 | 2 | 7 | TRUE
Fix Pipelines auto release | Development | 1 | 1 | 2 | 7 | TRUE
Implemnet unit tests for dynamic topic | Testing | 1 | 1 | 2 | 8 | TRUE
push/remove/get device content lambdas implmented and tested (ran into blockers related to iot, serverless, and travis ci) | Development | 3 | 10 | 2 | 8 | TRUE
meetings week 8 | Meeting | 3 | 2 | 2 | 8 | TRUE
Convert active content lambda to tv friendly format and unit test | Development | 2 | 1 | 2 | 8 | TRUE
instance id from android id | Development | 1 | 0.5 | 2 | 8 | TRUE
Helping others with stories | Development | 5 | 5 | 2 | 9 | TRUE
display qr codes on cards | Development | 4 | 4 | 2 | 9 | TRUE
attempt deploying on a Android TV device | Development | 4 | 4 | 2 | 9 | TRUE
restore push functionality to the web app | Development | 2 | 2 | 2 | 9 | TRUE
fix push to update active status | Development | 0.5 | 0.5 | 2 | 9 | TRUE
update cards to not be dimmed | Development | 1 | 1 | 2 | 10 | TRUE
fix 403 error on web app | Development | 4 | 4 | 2 | 10 | TRUE
content request lambdas and cloudformation limit fix | Development | 5 | 5 | 2 | 10 | TRUE
meetings week 10 | Meeting | 3 | 3 | 2 | 10 | TRUE
Research on adjusting fragment layouts to help aaron on smart tv | Research | 5 | 7 | 2 | 11 | TRUE
meetings week 11 | Meeting | 3 | 4 | 2 | 11 | TRUE
Changing smart tv qr content request implementation to dynamic | Development | 1 | 2 | 2 | 11 | TRUE
bug fixes for content request lambdas | Development | 1 | 3.5 | 2 | 11 | TRUE
research on custom card views for smart tv (no luck yet) | Research | 2 | 2 | 2 | 11 | TRUE
helping matt and aarron with db updates | Development | 1 | 1 | 2 | 11 | TRUE
Set up app on nvidia shield | Development | 2 | 2 | 2 | 12 | TRUE
Have web app register real devices | Development | 4 | 8 | 2 | 12 | TRUE
Device all deployed content | Development | 1 | 1 | 2 | 12 | TRUE
Content client id | Development | 1 | 1 | 2 | 12 | TRUE
Lambdas to limit gets by client and section id | Development | 4 | 5 | 2 | 12 | TRUE
smart tv pr bug fix | Development | 1 | 2 | 2 | 13 | TRUE
meetings week 13 | Meeting | 4 | 4 | 2 | 13 | TRUE
smart tv display title research | Research | 3 | 7 | 2 | 13 | TRUE
lambda bug fixes | Development | 2 | 4 | 2 | 13 | TRUE
smart tv display pictures research | Research | 3 | 4 | 2 | 13 | TRUE
verify all items are listed in swagger | Documentation | 1 | 2 | 2 | 13 | TRUE
work on poster | Presentation | 2 | 2 | 2 | 14 | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Philip
Task | Task Type | EST | ACT | Term | Week | Done
Attended a Meeting | Meeting | 1 | 3 | 1 | 1 | TRUE
| Research | 2 | 4 | 1 | 1 | TRUE
| Meeting | 3 | 3 | 1 | 2 | TRUE
| Documentation | 3 | 2 | 1 | 2 | TRUE
| Documentation | 2 | 1 | 1 | 2 | TRUE
| Modeling | 3 | 1 | 1 | 3 | TRUE
| Design | 2 | 3 | 1 | 3 | TRUE
| Documentation | 2 | 4 | 1 | 3 | TRUE
| Meeting | 3 | 3 | 1 | 3 | TRUE
| Meeting | 3 | 3 | 1 | 4 | TRUE
| Modeling | 3 | 3 | 1 | 4 | TRUE
| Meeting | 3 | 3 | 1 | 5 | TRUE
| Modeling | 1 | 0.5 | 1 | 5 | TRUE
| Documentation | 1 | 1 | 1 | 5 | TRUE
| Design | 1 | 1 | 1 | 5 | TRUE
| Meeting | 3 | 3 | 1 | 6 | TRUE
| Documentation | 1 | 1 | 1 | 6 | TRUE
| Documentation | 1 | 1 | 1 | 6 | TRUE
| Documentation | 2 | 3 | 1 | 6 | TRUE
| Modeling | 1 | 1 | 1 | 6 | TRUE
| Meeting | 3 | 3 | 1 | 7 | TRUE
| Process | 2 | 2.5 | 1 | 7 | TRUE
| Documentation | 1 | 0.5 | 1 | 7 | TRUE
| Modeling | 1 | 0.5 | 1 | 7 | TRUE
| Documentation | 1 | 1 | 1 | 7 | TRUE
| Meeting | 3 | 3 | 1 | 8 | TRUE
| Development | 1 | 2 | 1 | 8 | TRUE
| Documentation | 1 | 1 | 1 | 9 | TRUE
| Modeling | 1 | 1 | 1 | 9 | TRUE
| Meeting | 3 | 3 | 1 | 9 | TRUE
| Meeting | 3 | 3 | 1 | 10 | TRUE
| Documentation | 2 | 2 | 1 | 11 | TRUE
| Process | 1 | 1 | 1 | 11 | TRUE
| Modeling | 1 | 0.5 | 1 | 11 | TRUE
| Development | 1 | 1 | 1 | 11 | TRUE
| Development | 1 | 2 | 1 | 11 | TRUE
| Documentation | 0.5 | 0.5 | 1 | 11 | TRUE
| Process | 1 | 1 | 1 | 11 | TRUE
| Meeting | 3 | 3 | 1 | 11 | TRUE
| Development | 3 | 5 | 1 | 12 | TRUE
| Development | 1 | 3 | 1 | 13 | TRUE
| Presentation | 1 | 3 | 1 | 13 | TRUE
| Meeting | 2 | 3.5 | 1 | 14 | TRUE
| Process | 2 |  |  |  | FALSE
| Meeting | 2 | 1 | 2 | 2 | TRUE
| Documentation | 1 | 0.5 | 2 | 1 | TRUE
| Research | 1 | 1.5 | 2 | 2 | TRUE
| Development | 1 | 1 | 2 | 2 | TRUE
| Documentation | 1 | 1 | 2 | 1 | TRUE
| Documentation | 0.5 | 0.5 | 2 | 2 | TRUE
| Meeting | 2.5 | 2.75 | 2 | 2 | TRUE
| Research | 8 | 6 | 2 | 2 | TRUE
| Development | 6 | 7 | 2 | 2 | TRUE
| Meeting | 1 | 1.5 | 2 | 2 | TRUE
| Meeting | 1.5 | 3 | 2 | 3 | TRUE
| Meeting | 1.5 | 1.5 | 2 | 3 | TRUE
| Development | 5 | 4 | 2 | 3 | TRUE
| Meeting | 1.5 | 1.5 | 2 | 4 | TRUE
block unauthenticated users from logging in; List view for all clients | Development | 1 | 2 | 2 | 4 | TRUE
Figure out IoT topic architecture throughout the system - For registration and pushing content | Research | 5 | 3 | 2 | 4 | TRUE
Document IoT topic architecture | Documentation | 3 | 2 | 2 | 4 | TRUE
| Meeting | 1.5 | 1.5 | 2 | 4 | TRUE
| Meeting | 1.5 | 2 | 2 | 5 | TRUE
| Meeting | 1.5 | 2 | 2 | 5 | TRUE
| Development | 2 | 2 | 2 | 5 | TRUE
Updated Document after discussion | Documentation | 1 | 1.5 | 2 | 5 | TRUE
| Meeting | 1.5 | 2 | 2 | 6 | TRUE
| Meeting | 1.5 | 1.5 | 2 | 6 | TRUE
Modified db schema; updated db schema; setup classes for device functionality and wrote and unit tested device lambda | Development | 4 | 5 | 2 | 6 | TRUE
Wrote section lambdas and tested them.created UI for section and device viewing; updated API doc and deployed lambdas | Development | 3 | 5 | 2 | 6 | TRUE
Finished tying together the section and device functionality and tied services to the UI; Updated connection loading on smart tv | Development | 5 | 6 | 2 | 6 | TRUE
Documented new flow for lambdas and iot publishes/subscriptions | Documentation | 1 | 1 | 2 | 6 | TRUE
| Meeting | 1.5 | 1.25 | 2 | 7 | TRUE
Sprint 7 Demo | Meeting | 1.5 |  | 2 | 7 | TRUE
Made wireframes for Viewing and Approving/Denying Content Requests | Modeling | 2 | 4 | 2 | 7 | TRUE
Made wireframes for Creating and Editing a Section | Modeling | 2 | 2 | 2 | 7 | TRUE
Made wireframes for Assigning admin to client accounts and section accounts | Modeling | 2 | 1 | 2 | 7 | TRUE
Bug fixes | Development | 1 | 1 | 2 | 7 | TRUE
Bug investigation | Research | 2 | 2 | 2 | 7 | TRUE
Change the query return type in the lambda functions | Development | 1 | 0.5 | 2 | 7 | TRUE
Upload the new db schema to mysql | Development | 1 |  | 2 | 7 | TRUE
Refactor lambda structure | Development | 2 |  | 2 | 7 | TRUE
Updated db schema | Development | 1 | 1 | 2 | 8 | TRUE
Materialized content page | Development | 3 | 4 | 2 | 8 | TRUE
Investigated loading time bug/found solution | Development | 1 | 1 | 2 | 8 | TRUE
Team meeting | Meeting | 1.5 | 0.75 | 2 | 8 | TRUE
Sponsor meeting | Meeting | 2 | 2 | 2 | 8 | TRUE
| Development | 7 | 10 | 2 | 9 | TRUE
| Meeting | 1.5 | 1.5 | 2 | 9 | TRUE
| Meeting | 1.5 | 2 | 2 | 9 | TRUE
Finished jira items | Development | 9 | 16 | 2 | 10 | TRUE
Regular team meeting | Meeting | 1.5 | 2 | 2 | 10 | TRUE
Meeting with sponsor | Meeting | 1.5 | 2 | 2 | 10 | TRUE
Outside meeting with team; Changed lambdas to accept json - refactored some functions. Added details page | Meeting | 4 | 6.5 | 2 | 10 | TRUE
Research deployment error for Matt | Research | 1 | 1 | 2 | 10 | TRUE
Research API calls for getting user attributes | Research | 4 | 6 | 2 | 11 | TRUE
Research API calls for listing all users | Research | 1 | 1 | 2 | 11 | TRUE
Fixed content request page bug; Content Request form; push content with option to select a device | Development | 5 | 8 | 2 | 11 | TRUE
Meeting with team (Project Review) | Meeting | 1.5 | 1.5 | 2 | 11 | TRUE
Meeting with sponsor | Meeting | 1.5 | 1.5 | 2 | 11 | TRUE
Research API calls for getting user attributes | Research | 4 | 3 | 2 | 12 | TRUE
Review infrastructure with matt | Documentation | 1 | 0.5 | 2 | 12 | TRUE
Meeting with team | Meeting | 1.5 | 1 | 2 | 12 | TRUE
Meeting with sponsor | Meeting | 1.5 | 2 | 2 | 12 | TRUE
Fixed push content bug; create/test list user lambda | Development | 5 | 8 | 2 | 12 | TRUE
PR reviews and approval; created and designed user list; active status button; user registration flow | Development | 12 | 30 | 2 | 13 | TRUE
Research how to confirm users and how to invite users to the application | Research | 4 | 4 | 2 | 13 | TRUE
Group meeting | Meeting | 1.5 | 2 | 2 | 13 | TRUE
Sponsor meeting/demo | Meeting | 1.5 | 2 | 2 | 13 | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Aaron
Task | Task Type | EST | ACT | Term | Week | Done
Attended a Meeting | Meeting | 1 | 3 | 1 | 1 | TRUE
Started the temporary domain model | Modeling | 3 | 3 | 1 | 1 | TRUE
Team Meeting 9/4/19 - Discussed Requirements and what the software should actually do. Discussed methodology. Discussed Cloud solutions. | Meeting | 1.5 | 1.5 | 1 | 2 | TRUE
Team Meeting 9/6/19 - Started Requirements Documentation, Assigned Team Roles, Selected Design Methodology | Meeting | 1.25 | 1.25 | 1 | 2 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 2 | TRUE
Messed with the architecture of cloud services | Research | 2 | 3 | 1 | 2 | TRUE
Updated the domain model | Modeling | 1 | 2 | 1 | 3 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 3 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 3 | TRUE
Create sequence diagrams | Modeling | 2 | 3 | 1 | 3 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 4 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 1 | 1 | 4 | TRUE
Updated Use Case Document | Documentation | 2 | 3 | 1 | 5 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 5 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 1 | 1 | 5 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 6 | TRUE
Worked on EC2 research | Research | 2 | 2 | 1 | 6 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 1 | 1 | 6 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 6 | TRUE
Create System Diagram | Modeling | 2 | 3 | 1 | 7 | TRUE
Create nonfunctiontal and functional requirements | Documentation | 2 | 3 | 1 | 8 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 1 | 1 | 8 | TRUE
Run through the creation of ERD | Documentation | 2 | 1 | 1 | 8 | TRUE
Group Meeting | Meeting | 1 | 1 | 1 | 9 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 1 | 1 | 9 | TRUE
Team Meeting | Process | 0.5 | 0.5 | 1 | 10 | TRUE
Researched on MQTT protocol | Research | 4 | 5 | 1 | 10 | TRUE
Mid-Term project review with Kal | Meeting | 1 | 1 | 1 | 10 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 0.5 | 0.5 | 1 | 10 | TRUE
Learning how an Amazon Button communicates with AWS IOT | Research | 2 | 4 | 1 | 10 | TRUE
Created wireframes for the smart tv application | Design | 2 | 3 | 1 | 11 | TRUE
Research on creating an android mobile app and implemented counter | Research | 3 | 4 | 1 | 11 | TRUE
Started developing the smart tv register activity | Development | 3 | 4 | 1 | 11 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 0.75 | 1 | 11 | TRUE
Redocumenting the use case for registering a device | Documentation | 2 | 4 | 1 | 12 | TRUE
Research on creating a mobile application with RxJava, RetroFit and Dagger 2 | Research | 4 | 4 | 1 | 12 | TRUE
Team Meeting | Meeting | 1 | 1 | 1 | 12 | TRUE
Info Kiosk Sponsor Meeting | Meeting | 1 | 0.75 | 1 | 12 | TRUE
Developed second tv registration activity | Development | 3 | 5 | 1 | 13 | TRUE
Research and Implement sample android pub sub application for connecting tv app to mqtt broker | Research | 4 | 6 | 1 | 13 | TRUE
Meet with Kal to discuss interim presentation | Meeting | 2 | 2 | 1 | 14 | TRUE
Created third activity to display tile layout | Development | 2 | 2 | 1 | 14 | TRUE
Interim presentation after Kals feedback | Presentation | 4 | 5 | 1 | 14 | TRUE
Finalizing details of the interim presentation | Meeting | 1 | 3 | 1 | 14 | TRUE
FALSE
Team Meeting to discuss what was last spoke on before the break | Meeting | 1 | 1 | 2 | 1 | TRUE
Worked on getting the connection of the smart tv app to AWS IOT | Development | 3 | 5 | 2 | 1 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1.5 | 2 | 1 | TRUE
Team Meeting to discuss project plan with Kal | Meeting | 1 | 1.5 | 2 | 2 | TRUE
Worked with phil on getting communication between the webapp and Iot using my personal acc | Development | 1 | 1.5 | 2 | 2 | TRUE
Finish up the integrating pieces document of how the mobile app communicates with the IOT | Process | 1 | 1 | 2 | 2 | TRUE
Team meeting to assign story points to the next sprint | Meeting | 1 | 1 | 2 | 2 | TRUE
Meet up with team to go through the architecture and running the smart tv app on their machines | Meeting | 2 | 5 | 2 | 3 | TRUE
Carried out demo with sponsor | Meeting | 3 | 3 | 2 | 4 | TRUE
Story Pointed sprint 7 | Meeting | 1 | 1 | 2 | 5 | TRUE
Carried out creation of sprint 6 test plan and running sprint 5 test plan | Documentation | 3 | 4 | 2 | 5 | TRUE
Worked on creating the smart tv app wireframes | Design | 3 | 4 | 2 | 6 | TRUE
Group meeting and discussion for registration of smart tv design as well as working on the jira stories assigned to me | Design | 5 | 5 | 2 | 6 | TRUE
Group meeting for week 6 | Meeting | 3 | 3 | 2 | 6 | TRUE
Worked on creating the smart tv app cards | Development | 2 | 2 | 2 | 7 | TRUE
More attempts at getting smart tv cards to work | Development | 2 | 3 | 2 | 7 | TRUE
Met up to discuss the approvals of our wireframes | Meeting | 1 | 1.5 | 2 | 7 | TRUE
Made progress with adding VerticalGridFragment to card activity, it now has a grid fragment using txt view | Development | 3 | 6 | 2 | 8 | TRUE
Worked on getting content reloaded onto the fragments as well as the status activity page | Development | 3 | 6 | 2 | 9 | TRUE
Worked on making sure the status page works with the topic it connects to | Development | 1 | 2 | 2 | 10 | TRUE
Meeting up with team to point and discuss routing of the status page | Meeting | 1 | 2 | 2 | 10 | TRUE
Met up with sponsor to demo the progress we made | Meeting | 1 | 1 | 2 | 10 | TRUE
Finished status activity | Development | 3 | 5 | 2 | 10 | TRUE
Worked on expanding the card and getting another qr code on the ImageCardView | Development | 6 | 12 | 2 | 10 | TRUE
Project Review with Kal | Meeting | 1 | 1 | 2 | 11 | TRUE
Team meeting | Meeting | 1 | 0.75 | 2 | 11 | TRUE
worked on getting a fixed qr code image on the card activity page | Development | 5 | 5 | 2 | 11 | TRUE
created test plan document for sprint 9 | Documentation | 1 | 1 | 2 | 11 | TRUE
Meeting with Bizcloud | Meeting | 1 | 2 | 2 | 11 | TRUE
Project Review with Kal about updated metrics | Meeting | 1 | 1 | 2 | 12 | TRUE
Meeting with Bizcloud | Meeting | 1 | 1 | 2 | 12 | TRUE
Creating a custom image card view that displays more of the title and description | Development | 3 | 12 | 2 | 12 | TRUE
Met up with team to discuss further details on the tv app and functional stories | Meeting | 1 | 2 | 2 | 13 | TRUE
Worked on the test plan for sprint 10 | Documentation | 1 | 2 | 2 | 13 | TRUE
Made changes to the poster | Presentation | 1 | 5 | 2 | 13 | TRUE
Worked on the documentation of smart tv code | Documentation | 2 | 3 | 2 | 14 | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE