## Sheet1
Task ID | Task | Owner | Start | End | Completed | Activity Type | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12 |  | Week 13 |  | Week 14 |  | Week 15 |  | Week 16
[7 empty] | 2018-08-26 | 2018-09-01 | 2018-09-02 | 2018-09-08 | 2018-09-09 | 2018-09-15 | 2018-09-16 | 2018-09-22 | 2018-09-23 | 2018-09-29 | 2018-09-30 | 2018-10-06 | 2018-10-07 | 2018-10-13 | 2018-10-14 | 2018-10-20 | 2018-10-21 | 2018-10-27 | 2018-10-28 | 2018-11-03 | 2018-11-04 | 2018-11-10 | 2018-11-11 | 2018-11-17 | 2018-11-18 | 2018-11-24 | 2018-11-25 | 2018-12-01 | 2018-12-02 | 2018-12-08 | 2018-12-09 | 2018-12-15
1 | Planning Phase |  | 2018-08-30 | 2018-09-19 | TRUE
1.1 | Kick-Off Meeting | Team | 2018-08-30 | 2018-08-30 | TRUE | Meeting
1.2 | Publish Time Tracking | Team | 2018-09-08 | 2018-09-08 | TRUE | Process
1.3 | Submit Project Synopsis | Team | 2018-09-15 | 2018-09-15 | TRUE | Documentation
1.4 | Submit first draft of project plan | Team | 2018-09-15 | 2018-09-15 | TRUE | Documentation
1.5 | Publish domain model | Team | 2018-09-22 | 2018-09-22 | TRUE | Modeling
1.6 | Mid-Term project review | Team | 2018-10-07 | 2018-10-18 | TRUE | Meeting
2 | Design Phase |  | 2018-09-20 | 2018-10-17 | TRUE
2.1 | Sequence Diagrams | Team | 2018-10-11 | 2018-10-18 | TRUE | Modeling
2.2 | Use Case Diagram | Team | 2018-10-11 | 2018-10-18 | TRUE | Modeling
2.3 | Functional and non-functional requirements | Team | 2018-10-11 | 2018-10-16 | TRUE | Documentation
2.4 | Architecture models | Team | 2018-10-11 | 2018-10-16 | TRUE | Modeling
2.5 | Data Model | Matt | 2018-10-11 | 2018-10-16 | TRUE | Modeling
3 | Sprint 1 |  | 2018-10-18 | 2018-10-31 | TRUE
3.1 | Design Mock-up | Matt | 2018-10-18 | 2018-10-23 | TRUE | Design
3.2 | Setup Angular app | Phil | 2018-10-18 | 2018-10-23 | TRUE | Development
3.3 | Non Functional UI | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.3.1 | Form for adding a system admin | Phil | 2018-10-18 | 2018-10-25 | TRUE | Development
3.3.2 | Login Form | Phil | 2018-10-18 | 2018-10-25 | TRUE | Development
3.3.3 | Form for adding a Domain/Client Account Holder | Phil | 2018-10-18 | 2018-10-25 | TRUE | Development
3.3.4 | Form for adding a domain | Phil | 2018-10-18 | 2018-10-25 | TRUE | Development
3.3.5 | Page for viewing domains | Phil | 2018-10-18 | 2018-10-25 | TRUE | Development
3.3.6 | Form for registering a device | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.3.7 | Page for viewing devices | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.3.8 | Form for creating content | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.3.9 | Page for viewing all content | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.3.10 | Button/Link to push content to a smart device | Phil | 2018-10-25 | 2018-11-01 | TRUE | Development
3.4 | Set up AWS Tools | Sponsor | 2018-10-18 | 2018-10-22 | TRUE | Development
3.4.1 | Setup S3 | Dan | 2018-10-22 | 2018-10-25 | TRUE | Development
3.4.3 | Setup API Gateway | Dan | 2018-10-22 | 2018-10-25 | TRUE | Development
3.4.5 | Setup Lambda | Dan | 2018-10-22 | 2018-10-22 | TRUE | Development
3.4.6 | RDS |  |  |  | TRUE | Development
3.4.7 | Bastian Host |  |  |  | TRUE | Development
3.4.8 | CloudFront |  |  |  | TRUE | Development
3.4.9 | Route53 |  |  |  | TRUE | Development
3.5 | Smart TV App Development Research | Aaron | 2018-10-18 | 2018-10-31 | TRUE | Research
4 | Sprint 2 |  | 2018-11-01 | 2018-11-14 | FALSE
4.3.1 | Decide on endpoint functionality | Team | 2018-11-12 | 2018-11-13 | TRUE | Design
4.3.2 | Come up with endpoints | Phil | 2018-11-08 | 2018-11-13 | TRUE | Documentation
4.4.3 | Create Swagger file | Phil | 2018-11-14 | 2018-11-14 | TRUE | Documentation
4.4 | Non functional Smart TV UI | Aaron | 2018-11-01 | 2018-11-14 | TRUE | Development
4.4.1 | Smart TV UI wireframe | Aaron |  |  | TRUE | Design
4.5 | Add/Update Use Cases | Team | 2018-11-13 | 2018-11-13 | TRUE | Documentation
4.5.1 | Register Smart TV | Aaron | 2018-11-13 | 2018-11-13 | TRUE | Development
4.5.2 | Add a Section | Phil | 2018-11-13 | 2018-11-13 | TRUE | Development
4.5.3 | Add a Section Administrator | Phil | 2018-11-13 | 2018-11-13 | TRUE | Development
4.6 | Add sequence diagrams | Team | 2018-11-13 | 2018-11-13 | FALSE | Modeling
4.7 | DB Schema as code | Team | 2018-11-13 | 2018-11-13 | TRUE | Development
4.9 | Discuss requirements and progress with Kal | Team | 2018-11-13 | 2018-11-13 | TRUE | Meeting
4.9 | Revisit Requirements & Documents | Team | 2018-11-08 | 2018-11-14 | TRUE | Documentation
4.9.1 | Change Domain/Client to Client in all documents | Team | 2018-11-13 | 2018-11-13 | TRUE | Documentation
4.9.4 | Revisit ERD x2 | Matt and Phil | 2018-11-08 | 2018-11-13 | TRUE | Modeling
4.10x | Upload web app to S3 (need to update) |  |  |  | TRUE | Development
4.9.2 | Add deliverable dates to Project Plan | Matt | 2018-11-13 | 2018-11-15 | TRUE | Documentation
5 | Sprint 3 |  | 2018-11-15 | 2018-11-29 | FALSE
| Update Swagger file to have 2 API calls for device endpoints - one for Smart TV app and one for the web app | Phil |  |  | TRUE | Development
| Update the Use case for Register TV | Aaron |  |  | TRUE | Documentation
4.9.3 | Add features to project plan | Team | 2018-11-13 | 2018-11-15 | TRUE | Documentation
4.1 | Connect the frontend to API endpoints | Team | 2018-11-08 | 2018-11-19 | TRUE | Development
4.1.1 | Retrieve data using async get requests | Dan | 2018-11-08 | 2018-11-19 | TRUE | Development
4.1.2 | Add functions so that form send data to endpoint | Team | 2018-11-08 | 2018-11-19 | TRUE | Development
4.2 | Connect API Gateway endpoints to Lambda | Dan | 2018-11-08 | 2018-11-19 | TRUE | Development
4.3 | Write Lambda code | Dan | 2018-11-01 | 2018-11-19 | TRUE | Development
4.3.4 | Come up with lambda functions | Dan | 2018-11-01 | 2018-11-19 | TRUE | Development
5.1 | Setup IoT and Cognito | Team | 2018-11-15 | 2018-11-22 | TRUE | Development
5.2 | Connect Smart TV App to IoT channel | Team | 2018-11-22 | 2018-11-29 | FALSE | Development
5.3 | Interim Presentation (first draft) | Team | 2018-11-15 | 2018-11-22 | TRUE | Presentation
5.4 | Interim Presentation | Team | 2018-11-29 | 2018-11-29 | TRUE | Presentation
5.5 | Ensure Project Website is up-to-date | Matt | 2018-11-28 | 2018-11-28 | TRUE | Process
5.6 | Determine 2 Metrics | Team | 2018-11-13 | 2018-11-16 | TRUE | Process
5.7 | Update tracking report to account for these metrics | Phil | 2018-11-16 | 2018-11-19 | TRUE | Process
5.8 | Update SE website with updated project plan and metrics report | Matt | 2018-11-19 | 2018-11-19 | TRUE | Process
| Interim Self Assessment | Team | 2018-11-30 | 2018-12-04 | TRUE
| Schedule reflection meeting | Team | 2018-11-30 | 2018-12-04 | TRUE
| Peer evaluation | Team | 2018-11-30 | 2018-12-07 | TRUE
| Decide on Deliverable for next semester | Team | 2018-11-30 | 2018-12-07 | TRUE | Process

## Reference
Task Type | Members
Development | Matt
Documentation | Phil
Meeting | Aaron
Modeling | Dan
Presentation | Team
Research | Sponsor
Process | Matt and Phil
Design | Matt and Aaron
Matt and Dan
Phil and Aaron
Phil and Dan
Aaron and Dan
Matt, Phil and Aaron
Matt, Phil and Dan
Phil, Aaron and Dan