## SE361 Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Prevention Strategy | Migitation Plan | Status
1 | Challenges with integrating AWS and Smart-Tvs | 0.95 | high | 9.5 | Infrastructure | Daniel | Try to understand the core basics of Smart-Tv development before designing | Cycle back to the design phase and rework the system allowing for easier integration | Monitored
2 | Smart-TV development becomes more difficult than originally predicted | 0.8 | high | 8 | Developement | Philip | Do proper design critical research on Smart-Tvs before the design phase | Limit the scope in response to the amount of time remainnig and discuss with project sponsor | Monitored
3 | Communication with project sponsor declines over time resulting in misunderstood requirements. | 0.85 | medium | 4.25 | Stakeholders | Matt | Schedule additional meetings outside of the weekly check-in to maintain solid contact. | In addition to scheduling more meetings, find other forms of communicatiion such as sharing documents for feedback | Monitored
4 | Reliability on third party vendors that end up being unreliable. | 0.75 | medium | 3.75 | Technology | Aaron | Only use third party vendors that are reliable (ex. Amazon Web Services) | Find another resource with knowledge on the problem or find a new vendor | Monitored
5 | Integration with web application and Smart-Tv fails | 0.75 | low | 0.75 | Developement | Aaron | Research tools compatible with both web application and Smart-Tvs prior to design. | Use a different tool which is known to work with Smart-Tvs | Monitored
6 | Project sponsor tries to micromanage and presents unrealistic scope | 0.5 | medium | 2.5 | Stakeholders | Matt | Maintain strong communication with project sponsor to make sure both sides are aware of the scope and progress | Have a meeting to discuss changes with the project sponsor and create a document with agreed upon changes | Monitored
7 | Project sponsor requests different status report format from SE department. | 0.6 | low | 0.6 | Stakeholders | Daniel | Meetings with SE mentor in addition to project sponsor. | Use two different status reports to please both sides. | Monitored
8 | A key feature is not compatible with the system late in development stages. | 0.2 | high | 2 | Developement | Aaron | Release product in iterations so a basic features are in place early in development. | Cycle back to the design phase and rework the system. | Monitored
9 | Smart TV cannot connect to RIT wifi network. | 0.15 | low | 0.15 | Infrastructure | Philip | Confirm the Smart-Tv is compatible with RIT before allowing the project sponsor to purchase. | Purchase a new Smart-Tv or use a mobile hotspot. | Monitored
10 | AWS goes offline during outages. | 0.15 | low | 0.15 | Infrasturctue | Daniel | Keep the AWS infrastructure as code to prevent loss of information. | Bring up infrastructure in another region or wait for outage to end. | Monitored
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0
[10 empty] | Impact | Weight
0
[10 empty] | low | 1
[10 empty] | medium | 5
[10 empty] | high | 10